## Slide 1
Commencement of stage 1 for EIS phase 3
(Stage gates 1&2
Workstreams commence, nb both streams can run in paralell
Go / No go decision gate for formal testing with staff reps in attendance (Stage gate 3)
Commence works to reolve platfomr issues ie lighting
Workstream 2 Offciers special pre-test runs
Workstream 1 - Station risk assessments
Obtain hard copies of current Station RAs
RBS to check with NR Possession plan to enable optimum scope for route examination
RBS to ensure crew and test team booked for test run days
Updated RAs uploaded and distributed ready for Stage Gate 3.0
RBS to publish reports into observations made on officers special runs
Agree scope of works required with facilties/NR teams
RBS to visit each station site and validate RA content
RBS to work with TPU for pathways for 701 route assessment train
Where anomalies are identified, these are to be documented and added to tracker
Unit availability to be confirmed by RBS with Fleet planners for test run days
Amendments briefed and agreed with local SMs
Local SMs to meet and H&S reps to sign off amendments
Officers special to run on both a day and darkness run
RBS to check with NR Possession plan to enable optimum scope for route Assessment
RBS to work with TPU for pathways for 701 route assessment train
Unit availability to be confirmed by RBS with Fleet planners for 701 route assessment days
RBS to ensure crew and test team booked for 701 route assessment runs
Route assessment trains to run for each platform in each signalled direction on both a day and darkness run
RBS to collate and publish reports for results of each 701 assessment run
Submit reports to appropriate agencies for sign off and authorisation to commence operations
Where remedial works required, repeat stage gates 1-3 above as appropriate
Works complete and route signed into acceptance
701 Route Clearance Testing Readiness Check Process